## Sheet1
| Loxley NDP | Estimated timescale | 2016 |  |  |  | 2017 |  |  |  | 2018
| CRITICAL PATH | Weeks | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND | JFM | AMJ | JAS | OND
A | Issue identification
1 | Submit area for designation as NDP |  | 2016 JFM: Submitted
2 | Endorsement from SDC to proceed | 1 day
3 | Funding application and budgeting | 2
4 | Comms strategy (incl. social media) | 2
5 | Skills audit and formulate/establish working groups | 2
6 | Community meeting 1 - background & key issues | 1 day
7 | Interim report - outcomes from community meeting | 1 day
8 | Review past research - gap analysis | 1
9 | Review Census / ONS data | 1
10 | Initial meeting with SDC - confirm key designations | 1 day
11 | Optional : 'Twinning trip' / Learning from others event | 1 day | bar: 2016 JAS
B | Option analysis
12 | Develop questionnaire | 4
13 | Issue questionnaire / set up survey monkey | 4
14 | Analysis of results | 5
15 | Site identification and mapping | 2
16 | Community meeting 2 - survey results | 1 day
17 | Stakeholder consultations - politicians, schools, Parish Council, community groups etc. | 4
18 | Site appraisal (planning, highways, environment) | 8
19 | Community meeting 3 - site appraisal & key policies | 1 day
C | Plan preparation
20 | Develop vision, policies and objectives | 4
21 | Draft plan preparation and supporting maps | 4
22 | Optional : 'Health check' by independent third party | 2 | bar: 2017 OND
23 | Community meeting 4 - consult on draft plan | 1 day
24 | Stakeholder consultations on draft plan | 2
25 | Pre-submission publicity and consultation | 1
26 | Revisions to draft NDP | 2
27 | Submit to SDC for consideration | 1
28 | Publication of Neighbourhood Development Plan | 1
D | Examination and Referendum
29 | Appointment of Examiner | 1
30 | Contribute to Independent Examination | 4
31 | Council consider Examiner's recommendations | 2
32 | Publication of Examiner's Report | 1
33 | Publication of pre-referendum information statement and specified documents | 1
34 | Referendum | 4
35 | Publication of referendum decision and making of the Neighbourhood Development Plan
Key milestones
Loxley NDP Working Group - meetings
Version : 28th December 2015